## Event Marketing Timeline
WEST NILE PROJECT TIMELINE
RESPONSIBILITIES | DEADLINE | Status | NOTES
Background Research and Cost Benefit Analysis (Sian) | introductory slides describing West Nile and Chicago’s efforts to date. Preliminary estimates of the cost of spraying, and the benefits of preventing a West Nile outbreak | In Progress / Complete / Presentation Ready
Ugandan origins | Before Monday | Presentation ready
U.S. Cases | Before Monday | Presentation ready
Chicago Response | Before Monday | Presentation ready
Scenario 1: Outbreak CBA | Before Monday | Presentation ready
Scenario 2: Prevention CBA | Before Monday | Presentation ready
Slides and Summary | Monday - 3/5 | Presentation ready
EDA & Descriptive Analysis (Josh) | Scatterplots, graphs and maps describing the relationships in the data, and the pattern of previous sprayings, plus a verbal summary.
Provided datasets | Before Monday | Presentation ready
Outside datasets | Before Monday | Presentation ready
Graphs | Before Monday | Presentation ready | need graphs by week over week for temperature and humidity and windy
Maps | Before Monday | Presentation ready | year by year sprays, WNV, overlaid on the map of chicago
Written summary | Before Monday | Presentation ready
Turn in EDA | Monday - 3/5 | Presentation ready
Model Research & Preliminary Modeling (Zaheer, Sian) | A summary of feature extractions and models used on Kaggle, with the code used | A summary of feature extractions and models used on Kaggle, with the code used
Original and recent winners | Before Monday | Presentation ready
Provide best model and features | Monday - 3/5 | Presentation ready | Tuesday night completion
Modeling (Raj) | A fully cleaned and merged dataset; a code base for quickly running new models and saving the results; An initial basic model. | A fully cleaned and merged dataset; a code base for quickly running new models and saving the results; An initial basic model.
Greedy model | Monday - 3/5 | Presentation ready | Tuesday night completion
Complete codebase | Wednesday - 3/7 | Presentation ready | Raj will have it cleaned by 3/9
Presentation | A compelling, stunning and thorough presentation | A compelling, stunning and thorough presentation | 6
Inital Slides (Sian) | Monday - 3/5 | Presentation ready
Slides Complete | Wednesday - 3/7 | Presentation ready
Rehearsal | Thursday - 3/8 | Presentation ready
Turn it in | Friday - 3/9 - 9:30 am | Presentation ready
Final rehearsal | Friday - 3/9 - 9:40 am | Presentation ready
Victory |  | We won!
Web
Market Research
Surveys
Impact Studies
Sales Campaigns
Campaign A
Campaign B
Campaign C
Campaign D
Campaign E
Other
Corporate Branding
CLICK HERE TO CREATE EVENT MARKETING TIMELINE TEMPLATES IN SMARTSHEET